## Main
Preliminary Assessment | 855100
Permits & Approvals | 446948.3
Design & Engineering | 86393435
Financing & Procurement | 70000
Construction | 16234144
Validation | 4700000
TOTAL COSTS (Bottom Up) | 108699627.3
Final Cash Flow | All figures in AU $1mil
Tax rate | 30%
Cash Flow | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Capex | -108.6996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opex | 0 | -2.6418 | -2.7369 | -2.8354 | -2.9375 | -3.0433 | -3.1528 | -3.2663 | -3.3839 | -3.5057 | -3.6319
Revenue | 0 | 17.7046 | 18.342 | 19.0023 | 19.6864 | 20.3951 | 21.1293 | 20.58 | 20.0449 | 19.5237 | 19.0161
Government take | 0 | -4.5189 | -4.6815 | -4.8501 | -5.0247 | -5.2056 | -5.393 | -5.1941 | -4.9983 | -4.8054 | -4.6153
NCF | -108.6996 | 10.544 | 10.9236 | 11.3168 | 11.7242 | 12.1463 | 12.5836 | 12.1196 | 11.6627 | 11.2126 | 10.7689
Total NCF | -108.6996 | -98.1556 | -87.2321 | -75.9153 | -64.191 | -52.0447 | -39.4612 | -27.3416 | -15.6789 | -4.4663 | 6.3026
NPV
Discout Rate | 6%
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
NCF | -108.6996 | 10.544 | 10.9236 | 11.3168 | 11.7242 | 12.1463 | 12.5836 | 12.1196 | 11.6627 | 11.2126 | 10.7689
Discount Factor | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938 | 1.6895 | 1.7908
Present Values | -108.6996 | 9.9472 | 9.7219 | 9.5018 | 9.2867 | 9.0764 | 8.8709 | 8.0602 | 7.3173 | 6.6367 | 6.0133
Total NPV | -108.6996 | -98.7525 | -89.0305 | -79.5287 | -70.242 | -61.1656 | -52.2947 | -44.2345 | -36.9172 | -30.2805 | -24.2672

## Spider
Sheet Name | Cell | Adjustments | 0.8 | 0.82 | 0.84 | 0.86 | 0.88 | 0.9 | 0.92 | 0.94 | 0.96 | 0.98 | 1 | 1.02 | 1.04 | 1.06 | 1.08 | 1.1 | 1.12 | 1.14 | 1.16 | 1.18 | 1.2
Solar Production | P6 | Solar Value / MWh | 4.8396 | 4.9859 | 5.1322 | 5.2785 | 5.4248 | 5.5711 | 5.7174 | 5.8637 | 6.01 | 6.1563 | 6.3026 | 6.4489 | 6.5952 | 6.7415 | 6.8878 | 7.0341 | 7.1804 | 7.3267 | 7.473 | 7.6193 | 7.7656
Solar Production | P7 | Battery Discharge Value / MWh | -20.0404 | -17.4061 | -14.7718 | -12.1375 | -9.5032 | -6.8689 | -4.2346 | -1.6003 | 1.034 | 3.6683 | 6.3026 | 8.9369 | 11.5712 | 14.2055 | 16.8398 | 19.4741 | 22.1084 | 24.7427 | 27.377 | 30.0113 | 32.6456
Design & Engineering | H4 | Solar Panel Cost | 12.7826 | 12.1346 | 11.4866 | 10.8386 | 10.1906 | 9.5426 | 8.8946 | 8.2466 | 7.5986 | 6.9506 | 6.3026 | 5.6546 | 5.0066 | 4.3586 | 3.7106 | 3.0626 | 2.4146 | 1.7666 | 1.1186 | 0.47058 | -0.17742
Design & Engineering | H3 | Battery Cost | 13.6533 | 12.9182 | 12.1831 | 11.4481 | 10.713 | 9.9779 | 9.2429 | 8.5078 | 7.7727 | 7.0377 | 6.3026 | 5.5675 | 4.8324 | 4.0974 | 3.3623 | 2.6272 | 1.8922 | 1.1571 | 0.42203 | -0.31304 | -1.0481
Construction | H2 | Labour Cost | 8.8026 | 8.5526 | 8.3026 | 8.0526 | 7.8026 | 7.5526 | 7.3026 | 7.0526 | 6.8026 | 6.5526 | 6.3026 | 6.0526 | 5.8026 | 5.5526 | 5.3026 | 5.0526 | 4.8026 | 4.5526 | 4.3026 | 4.0526 | 3.8026
Operating Costs | N3 | Operating Cost | 10.6616 | 10.2257 | 9.7898 | 9.3539 | 8.918 | 8.4821 | 8.0462 | 7.6103 | 7.1744 | 6.7385 | 6.3026 | 5.8667 | 5.4308 | 4.9949 | 4.559 | 4.1231 | 3.6872 | 3.2513 | 2.8154 | 2.3795 | 1.9436

## Solar Production
https://www.endeavourenergy.com.au/news/media-releases/australian-energy-regulator-aer-published-endeavour-energy-regulatory-proposal-for-2024-2029
https://reneweconomy.com.au/anatomy-of-one-of-australias-first-solar-and-battery-hybrid-projects-the-costs-and-revenues/
Kerang Solar generation | Jan | Feb | March | April | May | June | July | August | September | October | November (2023) | December (2023) | Battery storage MWh | Battery Power | Charge discharge time (hrs)
Daily average solar generation for 10kW array (kWh) | 65.9 | 58.3 | 47.5 | 33.8 | 23.4 | 18.4 | 19.8 | 27.6 | 37.8 | 50.5 | 58.6 | 65.4 | 203.6 | 50.9 | 4
Scaled daily average solar generation for 100MW array (MWh) | 659 | 583 | 475 | 338 | 234 | 184 | 198 | 276 | 378 | 505 | 586 | 654
Full battery charges | 3.2367 | 2.8635 | 2.333 | 1.6601 | 1.1493 | 0.90373 | 0.9725 | 1.3556 | 1.8566 | 2.4804 | 2.8782 | 3.2122 | Wholesale Solar Scale | 1
Acheivable charge discharge cycles | 2 | 1.8 | 1.5 | 1.2 | 1 | 0.9 | 0.97 | 1.1 | 1.3 | 1.6 | 1.8 | 2 | Wholesale Battery Scale | 1
Wholesale Battery/day | 407.2 | 366.48 | 305.4 | 244.32 | 203.6 | 183.24 | 197.492 | 223.96 | 264.68 | 325.76 | 366.48 | 407.2
Wholesale Solar/day | 251.8 | 216.52 | 169.6 | 93.68 | 30.4 | 0.76 | 0.508 | 52.04 | 113.32 | 179.24 | 219.52 | 246.8
Month average solar value/MWh | 0.16 | 52.06 | 22.22 | 40.73 | 87.6 | 131.91 | 119.85 | 47.75 | 14.27 | -22.18 | 0.72 | -2.12
Month average battery value/MWh | 62.43 | 182.46 | 113.9 | 152.99 | 192.86 | 225.59 | 266.86 | 556.7 | 62.81 | 132.93 | 80.79 | 68.03
days of the month | 31 | 28.75 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
Month revenue ($k) | 789.3153 | 2246.5242 | 1195.1607 | 1235.8231 | 1299.8094 | 1243.1209 | 1635.6716 | 3942.0667 | 547.2488 | 1219.1597 | 892.9792 | 842.5366
Year 1 revenue ($M) | 17.0894

## Operating Costs
https://emp.lbl.gov/publications/benchmarking-utility-scale-pv
[12 empty] | Operation scale | 1
Estimated pricing (in 2019) of OpEx being ~US$17/kW/yr
Again, using currency conversion rate of 1.5AUD = 1USD (22/10)
Year | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
OpEx (AUD) | 2550000 | 2641800 | 2736904.8 | 2835433.373 | 2937508.974 | 3043259.297 | 3152816.632 | 3266318.031 | 3383905.48 | 3505726.077 | 3631932.216
OpEx (AUD) scaled | 2550000 | 2641800 | 2736904.8 | 2835433.373 | 2937508.974 | 3043259.297 | 3152816.632 | 3266318.031 | 3383905.48 | 3505726.077 | 3631932.216

## Top Down
| Lower Estimate | Upper Estimate
Preliminary Assessment | 800000 | 1000000
Permits & Approvals | 400000 | 500000
Design & Engineering | 80000000 | 100000000
Financing & Procurement | 50000 | 100000
Construction | 15000000 | 20000000
Validation | 4000000 | 6000000
TOTAL COSTS (Top down) | 100250000 | 127600000
Rounding | 100000000 | 127500000

## Preliminary Assessment
Preliminary Assessment
| Task | Cost Estimate | Link | Notes
Site Selection | Land Procurement | 552600 | https://www.domain.com.au/00-peacock-road-kerang-vic-3579-2018128282 | Acquisition of site at 00 Peacock Road
Surverying
| Boundaries and Zoning | 5000 |  | Cost of initial surveying, not inclusive of planning permit application
| Soil Testing | 2000
| Topography | 50000
| Irradiance Testing | 500 |  |  | 610100 | 57500
Feasibility Study | Technical Analysis | 60000 |  | Based off a team of 4 engineers working on this for 1-2 months, may need external consultation?
| Environmental Impact | 20000 |  | 2 weeks
| Infrastructure Assessment | 20000 |  | 2 weeks | 100000
Market Research | Risk Assessment | 30000 |  | 1-2 weeks
| Preliminary Project Report | 100000 |  | 1-2 months
| Demand Analysis | 15000 |  | 1-2 weeks | 145000
|  |  |  | Total Cost of Preliminary Assessment | 855100

## Permits & Approvals
Permits & Approvals
| Task | Cost Estimate | Link | Notes
Government | Local
| Planning Permits | 63589 | https://www.planning.vic.gov.au/guides-and-resources/legislation-regulation-and-fees/fees
| Construction Management Plan | 43359.3 | https://www.gannawarra.vic.gov.au/files/assets/public/v/1/document-resources/budgets/fees-and-charges-2023_24-adopted-15-march-2023.pdf | Strategic Planning Fees under the Planning and Environment (Fees) Regulations 2016 Considering Submissions and referral to Planning Panel (> 20 submissions)
State
| Renewable energy pre application | 5000 | https://www.google.com/url?sa=i&url=https%3A%2F%2Fwww.planning.vic.gov.au%2F__data%2Fassets%2Fword_doc%2F0012%2F622101%2Frenewable-energy-pre-application-form.docx&psig=AOvVaw27rDX2DYBNgeK_yrRZ1_vo&ust=1728623655854000&source=images&cd=vfe&opi=89978449&ved=0CAQQn5wMahcKEwiIwJDFh4OJAxUAAAAAHQAAAAAQBA | Pre-application form, leads to meeting with the Department of planning for approval for the project
| Landscaping Plan | 50000 | https://www.bookaarsolarfarm.com/wp-content/uploads/2023/03/Bookaar-Solar-Farm-Endorsed-Landscape-Plan.pdf | Document to consider the successful integration of the solar farm amoungst the development. Example doc given in link - will likely require external consulatation
| Traffic Management Plan | 20000 |  | Should be relatively simple considering remote location - will need to consider factors such as increased traffic on smaller local roads
| Wildlife Management Plan | 20000 | https://www.vic.gov.au/preparing-wildlife-management-plan | Will need to investigate how our plan of integrating sheep into the project will potentially effect existing wildlife populations
| Drainage and Stormwater Plan | 100000 | https://www.abc.net.au/news/2024-01-05/kerang-flash-flooding-stormwater-drainage-government/103281804 | Kerang is a town that can be prone to flooding due to it's location near to the Loddon River. This project should look to develop a high-quality drainage and stormwater plan as to be prepared for the event that the solar farm is subject to flooding, particularly as our farm generates electricity. External consulation will be required to ensure that this plan is watertight.
| Glare, Glint Light Spill Management Plan | 80000 | https://www.epa.wa.gov.au/sites/default/files/Referral_Documentation/Appendix%205%20-%20Reflective%20Glare%20Assessment%20%28SLR%2C%202022%29.pdf | Example document given for similar scale project. External consulation required
| Fire and Emergercy Management Plan | 20000
| Complaint Investigation and Response Plan | 10000
| EES | 0 | https://www.planning.vic.gov.au/environmental-assessments/browse-projects/referrals/fulham-solar-farm | Unlikely to be required in this project, see attached link 'Minister's decision on referral' | 305000
Federal
| AEIC Planning Permits | 10000 | https://www.aeic.gov.au/observations-and-recommendations/chapter-4-planning-permits | Would be able to use much of the same submission as previous planning permits, this is just a submission to a seperate body | 421948.3
Commercial | Grid Connection Approval | 20000
| Power Purchase Agreement | 5000 | https://www.environment.nsw.gov.au/resources/government/160416PPA%20explainer.pdf | Requires negotiation with energy providers so that we are well compensated for our electricity | 25000
|  |  |  | Total Cost of Permits & Approval | 446948.3

## Design & Engineering
Design & Engineering
| Task | Cost Estimate | Link | Notes |  | Battery scale | 1
Acquisition of Components | Electrical |  |  |  |  | Solar scale | 1
| Solar Panels | 32400000 | https://media.acciona.com.au/media/5346687/kerang-solar-farm-acciona-newsletter_feb18.pdf https://www.nrel.gov/solar/market-research-analysis/solar-manufacturing-cost.html | ~300 000 panels required for this project Price estimate of US$0.18/W manufacturing costs, will add 20% to this price to account for profit margin, shipping etc Assumption that 1.00USD is worth 1.50AUD (accurate at the time of writing - 16/10/2024) We will use Jinko Solar panels (most used in Australia), NEO meodel, produced in China
| Inverters | 7200000 | Inverter Requirements | Calculation for price of inverters linked
| Battery System | 36753435 | https://www.energy.vic.gov.au/about-energy/news/news-stories/koorangie-energy-storage-hits-major-milestone https://www.tesla.com/megapack/design | Cost of ordering 26 megapacks through Telsa for 50MW battery (supplier used in similar project in Gannawarra,that project was larger scale, using 100 packs)
| Grid Connection | 250000
| System Monitor | 50000
| Wiring | 500000 |  | cost of purchasing the wiring for the system
Mechanical
| Solar Tracking System | 9000000 | https://esolarfirst.en.made-in-china.com/product/ujemTCZOLVkA/China-Utility-Scale-Horizontal-Single-Axis-Solar-Tracking-System.html | The tracking system will cost US$0.06/W (lowest price assumed given large order, and will allow us to track the direction of the sun to maximise sun exposure The tracking system will be shipped from Fujian, China, from Xiamen Solar First Energy company. Assumption that 1.00USD is worth 1.50AUD (accurate at the time of writing - 16/10/2024) | 86153435
Site Layout | Panel Layout Design | 25000
Infrastructure Layout
| Inverter positioning and connection | 15000
| Battery integration | 30000
| Access Routing Design | 10000 |  |  | 80000
Electrical Design | Power Analysis | 50000
| Electrical Wiring and Connections | 60000
| Design Approval | 50000 |  |  | 160000
|  |  |  | Total Cost of Design & Engineering | 86393435

## Financing & Procurement
| Task | Cost Estimate | Link | Notes
Procurement Process | Tendering | 20000 |  | Bidding Process
| Purchase Agreements | 20000
| Supplier Assessment | 30000 |  | Need to investigate environmental effects and ethics of goods | 70000
Budgeting will not be included in pricing estimate as it will be managed by the salaried site managers
70000

## Construction
[6 empty] | Labour Scale | 1
| Task | Cost Estimate | Link | Notes
Build Project Workforce | Site Managers | 320000 |  | 2 site managers, hired of the duration of 12 months (project build time) Cost accounts for hiring process, wages, super, etc.
| Contractors | 2000000 |  | Budget allocated for contractors, likely in specilised work that has not already been accounted for in Preliminary Assessment.
| Labourers | 12500000 | https://media.acciona.com.au/media/5346687/kerang-solar-farm-acciona-newsletter_feb18.pdf | Similar project fot a 40MW farm in the same region saw the hiring of 50 full time construction staff. Scaling up for our project size, we will assume that we will need 125 staff for our 12 month construction phase Hired at an estimate of $100,000 each, including hiring costs and super etc.
| Training | 500000 |  | This budget will allow us to run training courses while we onboard our new staff. We will be able to reuse much of the training content from previous projects as our company Accionia has built multiple solar farms before | 14820000
Machinery and Equipment | Worker Facilities | 64144 | https://www.melbournetoilethire.com.au/toilet/toilets-portable/site-toilet-hire | cost of renting 8 porta potties for 12 months, as well as building a small permanent office building
| Machinery | 500000 |  |  | 564144
Construction | Site Preparation | 350000
| Operating costs (construction phase) | 500000 |  |  | 850000
|  |  |  | Total Cost of Construction | 16234144

## Validation
Task | Cost Estimate | Link | Notes
Compliance and Inspections | 1500000 |  | specification and safety checks
Testing | 3000000 |  | price of testing the system and fixing over 1.5-2 months period
Handover | 200000 |  | handover including monitoring of the system fo a period of 6 months | 4700000
|  |  | Total Cost of Validation | 4700000

## Inverter Requirements
SMA sunny central UP 4600
Cost of inverter (1 unit) | 240000
number of inverters (units) | 30
Inverter input voltage (V) | 1500
Number of Panels (units) | 300000
Panel Voltage | 12
Inverter output | 4600kw
String configuration | S | 125 | P | 80
Inverter cost ($AUD) | 7200000